## Product Backlog
User Story / Task / Requirement / Deliverable | Priority | Sprint planned | How long (hours) | Finished? | Issues with it?
Catalog user display | M | 1 | 12 | Y | Took longer than planned! 4 hours planned.
Database for catalog | M | 2 | 16 | Y | Planned for sprint 2 but didn't get to it until sprint 4.
Customer registration | M | 2 | 4 | Y | Done on time. No problems.
Work out barcode reader fn | M | 3 | 32 | N | On-going
Customer bookloans db | M | 4 | 16 | N | Not started
Link to catalog db | S | 4 | 16 | N | Not started -- may delay?
Catch up sprint! | C | 5 | 32 | N | Not started -- will decide if necessary when there!
Fine payment portal | M | 6 | 16 | N | Will delay until sprint 7 probably.
Online book renewal screens | S | 6 | 20 | N | Not started yet.

## Sprint Backlog 1
Sprint 1 | 04/11/19-15/11/19 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | Wireframes |  | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Use cases/flow diagrams |  | 4 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 5
| Sprint Planning |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Requirement | Team Invite QR Reading |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Team Invite QR Generation |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Team Invite |  | 8 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 8
| User Login |  | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Client Notification |  | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Team Display |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Team Modification |  | 4 |  | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 6
| Team Creation |  | 8 | 0 | 0 | 4 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 12
| Reflection |  | 3 | 0.5 |  | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 3
3. user story | Supervisor meeting 1 |  | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1
| Supervisor meeting 2 |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 50.5 | 45.45 | 40.4 | 35.35 | 30.3 | 25.25 | 20.2 | 15.15 | 10.1 | 5.05 | 0
Actual - remaining effort in Ideal hours |  |  | 50.5 | 38.5 | 38 | 23.5 | 23.5 | 20 | 12.5 | 5.5 | -1 | -1 | -1

## Sprint Backlog2
Sprint 1 | 18/11/19-29/11/19 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
Admin | sprint planning |  | 1 | [10 empty] | 1 | bar: Week 1 Mon
Feature | Task Viewing - Navigation |  | 4 | Week 1 Mon: 4 | 4
| Task Viewing - item render |  | 2 | Week 1 Wed: 1; Week 2 Mon: 2 | 3
| Task Viewing - list render |  | 2 | Week 1 Mon: 1; Week 1 Wed: 2 | 3
| Task Viewing - shared update |  | 2 | [10 empty] | 1 | bar: Week 1 Mon
Deliverable | UML Class Diagrams - Task creation, render, invite |  | 2 | Week 2 Wed: 3 | 3
| UML Class Diagrams - Team creation, render, invite |  | 2 | Week 2 Wed: 3 | 3
| Client-side validation -User |  | 2 | [10 empty] | 0
| Task - wireframes |  | 1 | [10 empty] | 1 | bar: Week 1 Tues
| Task - flow diagrams |  | 1 | Week 1 Tues: 2 | 2
| VIVA |  | 0.5 | Week 1 Thur: 0.5 | 0.5
| Supervisor Meeting |  | 0.5 | Week 1 Tues: 0.5
| Supervisor Meeting |  | 0.5 | [10 empty] | 0
| Task Creation |  | 4 | Week 1 Wed: 2; Week 2 Mon: 6 | 8
| Unit Testing |  | 4 | [10 empty] | 0
| Affordance UX based css |  | 2 | [10 empty] | 1 | bar: Week 1 Wed
| Reflection |  | 3 | Week 1 Mon: 0.5; Week 1 Tues: 0.5; Week 1 Wed: 0.5; Week 2 Mon: 0.5; Week 2 Wed: 0.5 | 2.5
| Jquery QR reader POC |  | 4 | Week 1 Wed: 4 | 4
Ideal - remaining work effort in Ideal hours |  |  | 37.5 | 33.75 | 30 | 26.25 | 22.5 | 18.75 | 15 | 11.25 | 7.5 | 3.75 | 0
Actual - remaining effort in Ideal hours |  |  | 37.5 | 30 | 26 | 15.5 | 15 | 15 | 6.5 | 6.5 | 0 | 0 | 0

## Sprint Backlog 3
Sprint 1 | 18/11/19-29/11/19 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
Admin | sprint planning |  | 1 | Week 1 Mon: 2 | 2
Feature | Client-side validation -Teams |  | 0.5 | Week 1 Tues: 2 | 2
| Task Completion(TC) - change status |  | 2 | Week 1 Tues: 2 | 2
| TC - respect requirements |  | 6 | Week 2 Mon: 4 | 4
| TC - give experience rewards |  | 6 | Week 1 Tues: 4 | 4
| TC - UI control |  | 1 | [10 empty] | 1 | bar: Week 1 Tues
Deliverable | UML Sequence Diagrams - team creation, render, invite |  | 4 | Week 2 Wed: 2; Week 2 Thur: 1 | 3
| UML Sequence Diagrams - task creation, render |  | 4 | Week 2 Wed: 2; Week 2 Thur: 1 | 3
| Database Schema |  | 1 | [10 empty] | 0
| Supervisor Meeting |  | 0.5 | [10 empty] | 0
| Supervisor Meeting |  | 0.5 | Week 2 Tues: 0.5 | 0.5
| Reflection |  | 3 | Week 1 Tues: 0.5; Week 2 Mon: 0.5; Week 2 Wed: 0.5; Week 2 Thur: 0.5 | 2
| Unit Testing |  | 2 | Week 2 Fri: 2 | 2
Ideal - remaining work effort in Ideal hours |  |  | 31.5 | 28.35 | 25.2 | 22.05 | 18.9 | 15.75 | 12.6 | 9.45 | 6.3 | 3.15 | 4.4409e-15
Actual - remaining effort in Ideal hours |  |  | 31.5 | 29.5 | 20 | 20 | 20 | 20 | 15.5 | 15 | 10.5 | 8 | 6

## Sprint Backlog 4
Sprint 1 | 16/12/2019-03/01/2020 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
| UX Form Input labels |  | 2 | Week 2 Mon: 2 | 2
| UX Task Completion Failure |  | 2 | Week 2 Mon: 2 | 2
| UX form helptext |  | 2 | Week 2 Mon: 2 | 2
| UX Empty Team / task list |  | 2 | Week 1 Mon: 2; Week 2 Mon: 2 | 4
| New User skill-list empty |  | 4 | Week 1 Tues: 6 | 6
| Database Scema Doc |  | 2 | [10 empty] | 0
| Create Questionair |  | 6 | Week 2 Mon: 3; Week 2 Thur: 1; Week 2 Fri: 2 | 6
| Finialise Aditional Features List |  | 1 | [10 empty] | 1 | bar: Week 2 Thur
| Reflection |  | 3 | Week 1 Mon: 0.5; Week 2 Mon: 0.5; Week 2 Fri: 0.5 | 1.5
| Sprint Planning |  | 0.5 | Week 1 Mon: 0.5 | 0.5
Ideal - remaining work effort in Ideal hours |  |  | 24.5 | 22.05 | 19.6 | 17.15 | 14.7 | 12.25 | 9.8 | 7.35 | 4.9 | 2.45 | 3.5527e-15
Actual - remaining effort in Ideal hours |  |  | 24.5 | 21.5 | 15.5 | 15.5 | 15.5 | 15.5 | 4 | 4 | 4 | 2 | -0.5

## Sprint Backlog 5
Sprint 1 | 06/01/2020-20/01/2020 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
| Sprint planning |  | 0.5 | Week 1 Mon: 0.5 | 0.5
| Supervisor meeting x2 |  | 1 | Week 1 Tues: 0.5 | 0.5
| User Page Experience Update |  | 4 | Week 1 Mon: 4 | 4
| Fanfare mechanic |  | 4 | Week 1 Mon: 3; Week 2 Mon: 1 | 4
| Level-up fanfair |  | 4 | Week 2 Mon: 2; Week 2 Tues: 1 | 3
| Reflection |  | 3 | [10 empty] | 3 | bar: Week 1 Mon; Week 2 Mon to Week 2 Tues
| Conduct Survey |  | 8 | Week 2 Tues: 2 | 2
| Skill Icons |  | 4 | Week 2 Mon: 3; Week 2 Tues: 1 | 4
| Information Arechecture |  | 2 | Week 2 Mon: 2 | 2
Ideal - remaining work effort in Ideal hours |  |  | 30.5 | 27.45 | 24.4 | 21.35 | 18.3 | 15.25 | 12.2 | 9.15 | 6.1 | 3.05 | -4.4409e-15
Actual - remaining effort in Ideal hours |  |  | 30.5 | 22 | 21.5 | 21.5 | 21.5 | 21.5 | 12.5 | 7.5 | 7.5 | 7.5 | 7.5

## Sprint Backlog 6
Sprint 1 | 20/01/2020-02/02/2020 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
| Sprint planning |  | 0.5 | Week 1 Mon: 0.5 | 0.5
| Conduct remaining surveys |  | 3 | Week 2 Mon: 1; Week 2 Fri: 2 | 3
| Requirements Display |  | 3 | Week 1 Wed: 2; Week 1 Fri: 1; Week 2 Tues: 2 | 5
| Deadline display |  | 1 | [10 empty] | 1 | bar: Week 1 Fri
| User access tests |  | 5 | Week 1 Tues: 4 | 4
| Teams access tests |  | 5 | [10 empty] | 2 | bar: Week 1 Tues to Week 1 Wed
| Tasks access tests |  | 5 | Week 1 Wed: 2 | 2
| Team types access |  | 3 | Week 1 Fri: 3 | 3
| Reflection |  | 3 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 |  |  |  | 0.5 | 3
0
Ideal - remaining work effort in Ideal hours |  |  | 28.5 | 25.65 | 22.8 | 19.95 | 17.1 | 14.25 | 11.4 | 8.55 | 5.7 | 2.85 | -4.4409e-15
Actual - remaining effort in Ideal hours |  |  | 28.5 | 27.5 | 22 | 16.5 | 16.5 | 11 | 9.5 | 7.5 | 7.5 | 7.5 | 5

## Sprint Backlog 6 (2)
Sprint 1 | 03/02/2020-14/02/2020 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
| Sprint planning |  | 0.5 | Week 1 Mon: 0.5 | 0.5
| Access Permissions users |  | 4 | Week 1 Thur: 2 | 2
| Access Permissions teams |  | 4 | Week 1 Thur: 2 | 2
| Access Permissions tasks |  | 4 | Week 1 Thur: 2 | 2
| Survey Breakdown |  | 3 | Week 1 Mon: 3 | 3
| Report writing |  | 10 | Week 2 Mon: 3; Week 2 Wed: 4; Week 2 Thur: 3 | 10
| Supervisor Meeting |  | 1 | Week 1 Tues: 0.5 | 0.5
| Reflection |  | 3 | Week 1 Mon: 0.5; Week 1 Tues: 0.5; Week 1 Thur: 0.5; Week 2 Mon: 0.5; Week 2 Wed: 0.5 | 2.5
| Edit Team iPhone bug |  | 2 | Week 1 Wed: 5 | 5
Ideal - remaining work effort in Ideal hours |  |  | 31.5 | 28.35 | 25.2 | 22.05 | 18.9 | 15.75 | 12.6 | 9.45 | 6.3 | 3.15 | 4.4409e-15
Actual - remaining effort in Ideal hours |  |  | 31.5 | 27.5 | 26.5 | 21.5 | 15 | 15 | 11.5 | 11.5 | 7 | 4 | 4