## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | PROJECT TITLE | [6 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 to AC2. | Company Name | [6 empty] | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. | Project Lead |  |  | Project Start Date: |  | 2019-11-04
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 to cell BL4. Do not modify these cells. They are auto-updated based on the project start date in cell F3. |  |  |  | Scrolling Increment: |  | 0 |  | November | [27 empty] | December
Cells I5 to BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto-calculated. Do not modify these cells. Today’s date is outlined in Red (hex #AD3815) from today’s date in row 5 through the entire date column to the end of the project schedule. | time axis 2019-11-04 to 2019-12-29
A scrollbar is in cells I6 to BL6. The increment for paging through the data is defined as 2 pages at a time and can be configured in the settings for the control bar. To jump forwards or backwards in the timeline, enter a value of 0 or higher in cell F4. A value of 0 takes you to the beginning of the chart.
This row contains headers for the project schedule that follows below them. Navigate from B7 to BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues to cell BL7. All project timeline charting is auto-generated based on the category, start date and number of days entered in the Milestones table. | Milestone description | Required | Category | Estimated Duration | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Release 1 |  | Milestone |  |  | 2019-12-29 | 1 | bar: S
| Sprint 1 |  |  |  |  | 2019-11-04 | 14
| User Login | Yes | Low risk | 4 | 100% | 2019-11-04 | 1
| Client Notification | Yes | Med risk | 8 | 100% | 2019-11-04 | 1
| Team Modification | Yes | Med risk | 8 | 100% | 2019-11-12 | 2
| Team Creation | Yes | Med risk | 8 | 100% | 2019-11-06 | 8
| Basic Team Display Page | Yes | Low risk | 2 | 100% | 2019-11-08 | 1
| Team Invite Notification | Yes | High risk | 8 | 100% | 2019-11-04 | 3
| Team Invite QR Reading | Yes | Low risk | 2 | shelved | 2019-11-11 | 1
| Team Invite QR Generation | Yes | Low risk | 2 | 100% | 2019-11-11 | 1
| Supervisor Meeting | Yes | Low risk | 0.5 | 100% | 2019-11-05 | 1
| Sprint Planning | Yes | Low risk | 0.5 | 100% | 2019-11-04 | 1
| Release Use cases / Flow | Yes | Low risk | 4 | 100% | 2019-11-07 | 1
| Release Wireframes | Yes | Low risk | 4 | 100% | 2019-11-04 | 0.5
| Unit Testing | Yes | Low risk | 4 | 100% | 2019-11-15 | 1
| Supervisor Meeting | Yes | Low risk | 0.5 | 100% | 2019-11-12 | 1
| Sprint 2 |  |  |  |  | 2019-11-18 | 14
| sprint planning | Yes | Low risk | 1 | 100% | 2019-11-18 | 1
| Task Viewing - Navigation | Yes | Med risk | 4 | 100% | 2019-11-18 | 1
| Task Viewing - item render | Yes | Low risk | 2 |  |  | 1
| Task Viewing - list render | Yes | Low risk | 2 | 100% | 2019-11-18 | 1
| Task Viewing - shared update | Yes | Low risk | 2 | 100% | 2019-11-18 | 1
| UML Diagrams - Task creation, render, invite | Yes | Low risk | 2 |  |  | 1
| UML Diagrams - Team creation, render, invite | Yes | Low risk | 2 |  |  | 1
| Client-side validation -User | Yes | Low risk | 2 |  |  | 1
| Task - wireframes | Yes | Low risk | 1 |  |  | 1
| Task - flow diagrams | Yes | Low risk | 1 |  |  | 1
| Supervisor Meeting | Yes | Low risk | 0.5 |  | 2019-11-19 | 1
| Supervisor Meeting | Yes | Low risk | 0.5 |  |  | 1
| Task Creation | Yes | Low risk | 4 |  |  | 1
| Unit Testing | Yes | Low risk | 4 |  |  | 1
| Jquery QR reader POC | Yes | Med risk | 4 |  |  | 1
| Affordance UX based css | Yes | Low risk | 2 |  |  | 1
| Sprint 3 |  |  |  |  | 2019-12-02 | 14
| Sprint 4 |  |  |  |  | 2019-12-16 | 14
| UML Diagrams | Yes | Low risk | 8 |  |  | 0.5
| Client-side validation -Task | Yes | Low risk | 4 |  |  | 0.5
| Client-side validation -User | Yes | Low risk | 4 |  |  | 0.5
| Database Schema | Yes | Low risk | 4 |  |  | 1
| User Stories | Yes | Low risk | 4 |  |  | 1
| Unit Testing x2 | Yes | Low risk | 8 |  |  | 1
| Supervisor Meeting x4 | Yes | Low risk | 4 |  |  | 1
| Sprint Planning x2 | Yes | Low risk | 2 |  |  | 1
| Reflection | Yes | Low risk | 12 |  |  | 3
| Contigency |  |  | 36
175.5
| Release 2 |  | Milestone |  |  | 2020-02-23 | 1
| Sprint 1 |  |  |  |  | 2019-12-30 | 14
| Sprint 2 |  |  |  |  | 2020-01-13 | 14
| Sprint 3 |  |  |  |  | 2020-01-27 | 14
| Sprint 4 |  |  |  |  | 2020-02-10 | 14
| Task Completion | Yes | Med risk | 12 |  |  | 1
| Task Rewards | Yes | Med risk | 12 |  |  | 3
| Access Permissions users | Yes | High risk | 6 |  |  | 4
| Access Permissions teams | Yes | High risk | 6 |  |  | 4
| Access Permissions tasks | Yes | High risk | 6 |  |  | 4
| Client-side Team Validation | Yes | Low risk | 4 |  |  | 0.5
| Teams Page | Yes | Low risk | 4 |  |  | 1
| Unit Testing | Yes | Low risk | 6 |  |  | 1
| Integration Testing | Yes | Med risk | 6 |  |  | 1
| UAT | Yes | Med risk | 6 |  |  | 1
| Supervisor Meeting x8 | Yes | Low risk | 4 |  |  | 1
| Sprint Planning x4 | Yes | Low risk | 2 |  |  | 1
| Reflection | Yes | Low risk | 12 |  |  | 3
| Contigency |  |  | 44
130
| Release 3 |  | Milestone |  |  | 2020-04-20 | 1
| Sprint 1 |  |  |  |  | 2020-02-24 | 14
| Sprint 2 |  |  |  |  | 2020-03-09 | 14
| Sprint 3 |  |  |  |  | 2020-03-23 | 14
| Sprint 4 |  |  |  |  | 2020-04-06 | 14
| Team Notification | No | Med risk | 8 |  |  | 2
| Styling | No | Low risk | 6 |  |  | 2
| Animations | No | Low risk | 8 |  |  | 2
| Finallising Report | Yes | Low risk | 24 |  |  | 7
| UAT | Yes | Med risk | 6 |  |  | 1
| Reflection | Yes | Low risk | 12 |  |  | 3
| Supervisor Meeting x8 | Yes | Low risk | 4 |  |  | 1
| Sprint Planning x4 | Yes | Low risk | 2 |  |  | 1
| Hardening | Yes | Low risk | 12 |  |  | 3
| Contigency |  |  | 46
128
This is an empty row
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add more data, Insert new rows ABOVE this one

## About
About this template
This template provides a simple way to create a Gantt chart to help visualise and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a per cent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is colour-coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for screen readers
There are two worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you to the information in that row. Each subsequent step continues in cell A2, A3 and so on, unless otherwise explicitly directed. For example, instruction text might say “continue to cell A6” for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.