## Product Backlog
User Story / Task / Requirement / Deliverable | Priority | Sprint planned | How long (hours) | Finished? | Issues with it?
Catalog user display | M | 1 | 12 | Y | Took longer than planned! 4 hours planned.
Database for catalog | M | 2 | 16 | Y | Planned for sprint 2 but didn't get to it until sprint 4.
Customer registration | M | 2 | 4 | Y | Done on time. No problems.
Work out barcode reader fn | M | 3 | 32 | N | On-going
Customer bookloans db | M | 4 | 16 | N | Not started
Link to catalog db | S | 4 | 16 | N | Not started -- may delay?
Catch up sprint! | C | 5 | 32 | N | Not started -- will decide if necessary when there!
Fine payment portal | M | 6 | 16 | N | Will delay until sprint 7 probably.
Online book renewal screens | S | 6 | 20 | N | Not started yet.

## Sprint Backlog 1
Sprint 1 | 04/11/19-15/11/19 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | Wireframes |  | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Use cases/flow diagrams |  | 4 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 5
| Sprint Planning |  | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Requirement | Team Invite QR Reading |  | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1
| Team Invite QR Generation |  | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2
| Team Invite |  | 8 | 2 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 8
| User Login |  | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| Client Notification |  | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| Team Display |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| Team Modification |  | 4 |  | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 6
| Team Creation |  | 8 | 0 | 0 | 4 | 0 | 0 | 4 | 2 | 2 | 0 | 0 | 12
3. user story | Supervisor meeting 1 |  | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1
| Supervisor meeting 2 |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  | 47.5 | 42.75 | 38 | 33.25 | 28.5 | 23.75 | 19 | 14.25 | 9.5 | 4.75 | 0
Actual - remaining effort in Ideal hours |  |  | 47.5 | 36 | 35.5 | 21.5 | 21.5 | 18.5 | 11.5 | 5 | -1 | -1 | -1

## Sprint Backlog 1 (2)
Sprint 1 | 18/11/19-29/11/19 |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
Admin | sprint planning |  | 1 | [10 empty] | 1 | bar: Week 1 Mon
Feature | Task Viewing - Navigation |  | 4 | Week 1 Mon: 4 | 4
| Task Viewing - item render |  | 2 | [10 empty] | 1 | bar: Week 1 Wed
| Task Viewing - list render |  | 2 | Week 1 Mon: 1; Week 1 Wed: 2 | 3
| Task Viewing - shared update |  | 2 | [10 empty] | 1 | bar: Week 1 Mon
Deliverable | UML Diagrams - Task creation, render, invite |  | 2 | [10 empty] | 0
| UML Diagrams - Team creation, render, invite |  | 2 | [10 empty] | 0
| Client-side validation -User |  | 2 | [10 empty] | 0
| Task - wireframes |  | 1 | [10 empty] | 1 | bar: Week 1 Tues
| Task - flow diagrams |  | 1 | Week 1 Tues: 0.5 | 0.5
| Supervisor Meeting |  | 0.5 | Week 1 Tues: 0.5
| Supervisor Meeting |  | 0.5 | [10 empty] | 0
| Task Creation |  | 4 | Week 1 Wed: 2 | 2
| Unit Testing |  | 4 | [10 empty] | 0
| Affordance UX based css |  | 2 | bar: Week 1 Wed
| Jquery QR reader POC |  | 4 | Week 1 Wed: 4 | 4
Ideal - remaining work effort in Ideal hours |  |  | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 6.2172e-15
Actual - remaining effort in Ideal hours |  |  | 34 | 27 | 25 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15

## Sprint Backlog 2
Sprint 2 | 5/3/2017-17/3/2017 |  |  |  |  | Week 1 |  |  |  |  | Week 2
User Story/ Requirement / Feature / Deliverable | Task | Priotity | Originator | Responsible | Estimate Effort hours | Mon | Tues | Wed | Thur | Fri | Mon | Tues | Wed | Thur | Fri | Actual effort per task
1. Iteration Planning | 1.1 Planning with Product Owner | Must | ScrumMaster | ScrumMaster | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
| 1.2. Detailed planning with Team | Must | ScrumMaster | Team | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2. Add to basket user story |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal - remaining work effort in Ideal hours |  |  |  |  | 8 | 7.2 | 6.4 | 5.6 | 4.8 | 4 | 3.2 | 2.4 | 1.6 | 0.8 | 1.1102e-15
Actual - remaining effort in Ideal hours |  |  |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0